## Triage
S1 Rehearsal Reject Triage — Generated August 17, 2026
Loader | Latest Run Date | Outcome | Reject Reason | Count (Latest Run) | Count Trend (oldest → newest) | Triage Category | Review Status | Allow-list? | Owner | Decision / Notes | Follow-up Ref
56 triage rows total ¦ Rows sorted: largest reject count first; resolved/no-rejects at bottom
t17-benefit-history | 8/9/2026, 4:33:32 PM | verified | relation_unmapped | 71964 | 71964 → 71964 → 71964 |  | Not reviewed
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | verified | worker_id_value_collision | 17107 | 17107 |  | Not reviewed
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | verified | duplicate_email | 10614 | 10614 |  | Not reviewed
t17-benefit-history | 8/9/2026, 4:33:32 PM | verified | benefit_unmapped | 6863 | 6863 → 6863 → 6863 |  | Not reviewed
t17-benefit-history | 8/9/2026, 4:33:32 PM | verified | end_before_start | 2553 | 2553 → 2553 → 2553 |  | Not reviewed
t17-benefit-history | 8/9/2026, 4:33:32 PM | verified | employer_unresolved | 1462 | 35103 → 1462 → 1462 |  | Not reviewed
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | verified | address_incomplete | 1089 | 1089 |  | Not reviewed
t16-elections | 8/9/2026, 11:29:39 AM | verified | end_not_after_start | 625 | 625 → 625 → 625 |  | Not reviewed
t17-benefit-history | 8/9/2026, 4:33:32 PM | verified | worker_unmapped | 452 | 452 → 452 → 452 |  | Not reviewed
t7t24-employers | 8/8/2026, 5:43:19 PM | verified | duplicate_email | 442 | 442 → 442 |  | Not reviewed
t27-users | 8/8/2026, 5:36:00 PM | verified | no_resolvable_worker | 335 | 335 |  | Not reviewed
t16-elections | 8/9/2026, 11:29:39 AM | verified | worker_unmapped | 234 | 234 → 234 → 234 |  | Not reviewed
t-policies | 8/8/2026, 5:07:27 PM | verified | policy_unmatched_unreferenced | 129 | 129 → 129 |  | Not reviewed
t19-payments | 8/8/2026, 7:17:26 PM | verified | amount_missing | 102 | 102 → 102 |  | Not reviewed
n4-employee-ids | 8/8/2026, 6:31:15 PM | verified | worker_unmapped | 80 | 80 → 80 |  | Not reviewed
t7t24-employers | 8/8/2026, 5:43:19 PM | verified | shopcontact_no_name | 73 | 73 → 73 |  | Not reviewed
t17-benefit-history | 8/9/2026, 4:33:32 PM | verified | subscriber_worker_mismatch | 69 | 69 → 69 → 69 |  | Not reviewed
t16-elections | 8/9/2026, 11:29:39 AM | verified | benefit_unmapped | 54 | 54 → 54 → 54 |  | Not reviewed
t15-relationships | 8/8/2026, 6:50:15 PM | verified | owner_has_no_worker | 42 | 42 → 42 |  | Not reviewed
t17-benefit-history | 8/9/2026, 4:33:32 PM | verified | benefit_ref_missing | 41 | 41 → 41 → 41 |  | Not reviewed
t19-payments | 8/8/2026, 7:17:26 PM | verified | payer_ref_missing | 40 | 40 → 40 |  | Not reviewed
t27-users | 8/8/2026, 5:36:00 PM | verified | ambiguous_worker_email | 26 | 26 |  | Not reviewed
t16-elections | 8/9/2026, 11:29:39 AM | verified | relation_unmapped | 22 | 22 → 22 → 22 |  | Not reviewed
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | verified | phone_invalid | 21 | 21 |  | Not reviewed
t17-benefit-history | 8/9/2026, 4:33:32 PM | verified | start_missing | 16 | 16 → 16 → 16 |  | Not reviewed
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | verified | contact_no_name | 9 | 9 |  | Not reviewed
t15-relationships | 8/8/2026, 6:50:15 PM | verified | alt_worker_unmapped | 7 | 7 → 7 |  | Not reviewed
t7t24-employers | 8/8/2026, 5:43:19 PM | verified | phone_invalid | 7 | 7 → 7 |  | Not reviewed
t15-relationships | 8/8/2026, 6:50:15 PM | verified | relation_create_failed | 6 | 6 → 6 |  | Not reviewed
t7t24-employers | 8/8/2026, 5:43:19 PM | verified | shopcontact_employer_unresolved | 5 | 5 → 5 |  | Not reviewed
n4-employee-ids | 8/8/2026, 6:31:15 PM | verified | employer_unmapped | 4 | 4 → 4 |  | Not reviewed
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | verified | worker_contact_unresolved | 4 | 4 |  | Not reviewed
t16-elections | 8/9/2026, 11:29:39 AM | verified | start_missing | 3 | 3 → 3 → 3 |  | Not reviewed
t16-elections | 8/9/2026, 11:29:39 AM | verified | worker_ref_missing | 3 | 3 → 3 → 3 |  | Not reviewed
t19-payments | 8/8/2026, 7:17:26 PM | verified | status_missing | 3 | 3 → 3 |  | Not reviewed
t19-payments | 8/8/2026, 7:17:26 PM | verified | account_unensured | 3 | 3 → 3 |  | Not reviewed
n21-call-logs | 8/11/2026, 4:14:24 PM | verified | handler_dangling | 2 | 0 → 2 → 2 → 2 → 2 |  | Not reviewed
t-employer-policies | 8/8/2026, 10:13:52 PM | verified | policy_unmapped | 2 | 2 → 2 |  | Not reviewed
t-employer-rates | 8/8/2026, 10:20:32 PM | verified | bad_rate | 2 | 2 → 2 |  | Not reviewed
t15-relationships | 8/8/2026, 6:50:15 PM | verified | alt_contact_unmapped | 2 | 2 → 2 |  | Not reviewed
t16-elections | 8/9/2026, 11:29:39 AM | verified | employer_ref_missing | 2 | 2 → 2 → 2 |  | Not reviewed
t-employer-rates | 8/8/2026, 10:20:32 PM | verified | rate_conflict | 1 | 1 → 1 |  | Not reviewed
t-policies | 8/8/2026, 5:07:27 PM | verified | policy_ref_not_staged | 1 | 1 → 1 |  | Not reviewed
t19-payments | 8/8/2026, 7:17:26 PM | verified | date_missing | 1 | 1 → 1 |  | Not reviewed
t19-payments | 8/8/2026, 7:17:26 PM | verified | payment_type_missing | 1 | 1 → 1 |  | Not reviewed
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | verified | ssn_collision_q36 | 1 | 1 |  | Not reviewed
t6-member-statuses | 8/8/2026, 5:35:55 PM | verified | worker_unmapped | 1 | 1 |  | Not reviewed
n21-call-logs | 8/11/2026, 4:14:24 PM | verified | category_unmapped | 0 | 700 → 7 → 2 → 0 → 0 (resolved) |  | Not reviewed
n21-call-logs | 8/11/2026, 4:14:24 PM | verified | handler_unresolved | 0 | 9202 → 0 → 0 → 0 → 0 (resolved) |  | Not reviewed
seed-trust-config | 8/8/2026, 4:42:17 PM | completed | (no rejects) |  | none in all runs |  | Not reviewed
t16-elections | 8/9/2026, 11:29:39 AM | verified | election_type_unmapped | 0 | 61823 → 0 → 0 (resolved) |  | Not reviewed
t17-benefit-history | 8/9/2026, 4:33:32 PM | verified | open_end_through_required | 0 | 159735 → 0 → 0 (resolved) |  | Not reviewed
t18-ledger | 8/8/2026, 6:26:05 PM | verified | (no rejects) |  | none in all runs |  | Not reviewed
t20-hours | 8/9/2026, 5:08:00 PM | completed | (no rejects) |  | none in all runs |  | Not reviewed
t29-enrollment-packet-tags | 8/11/2026, 4:17:53 PM | verified | (no rejects) |  | none in all runs |  | Not reviewed
t4-options | 8/8/2026, 1:43:24 PM | verified | (no rejects) |  | none in all runs |  | Not reviewed

## Run History
S1 Rehearsal — Full Run History (all runs, all reject reasons)
Loader | Started | Duration | Outcome | Reject Reason | Count
t29-enrollment-packet-tags | 8/11/2026, 4:17:53 PM | 133.2s | verified | (none)
n21-call-logs | 8/11/2026, 4:14:24 PM | 111.5s | verified | handler_dangling | 2
n21-call-logs | 8/11/2026, 4:08:09 PM | 169s | verified | handler_dangling | 2
n21-call-logs | 8/11/2026, 1:31:13 PM | 182.7s | verified | handler_dangling | 2
n21-call-logs | 8/11/2026, 1:31:13 PM | 182.7s | verified | category_unmapped | 2
n21-call-logs | 8/11/2026, 12:59:54 PM | 406.8s | verified | handler_dangling | 2
n21-call-logs | 8/11/2026, 12:59:54 PM | 406.8s | verified | category_unmapped | 7
n21-call-logs | 8/11/2026, 11:44:29 AM | 61.8s | verified | category_unmapped | 700
n21-call-logs | 8/11/2026, 11:44:29 AM | 61.8s | verified | handler_unresolved | 9202
t29-enrollment-packet-tags | 8/11/2026, 10:30:03 AM | 83.4s | verified | (none)
t20-hours | 8/9/2026, 5:08:00 PM | 142557.4s | completed | (none)
t17-benefit-history | 8/9/2026, 4:33:32 PM | 1263.7s | verified | start_missing | 16
t17-benefit-history | 8/9/2026, 4:33:32 PM | 1263.7s | verified | worker_unmapped | 452
t17-benefit-history | 8/9/2026, 4:33:32 PM | 1263.7s | verified | benefit_unmapped | 6863
t17-benefit-history | 8/9/2026, 4:33:32 PM | 1263.7s | verified | end_before_start | 2553
t17-benefit-history | 8/9/2026, 4:33:32 PM | 1263.7s | verified | relation_unmapped | 71964
t17-benefit-history | 8/9/2026, 4:33:32 PM | 1263.7s | verified | benefit_ref_missing | 41
t17-benefit-history | 8/9/2026, 4:33:32 PM | 1263.7s | verified | employer_unresolved | 1462
t17-benefit-history | 8/9/2026, 4:33:32 PM | 1263.7s | verified | subscriber_worker_mismatch | 69
t17-benefit-history | 8/9/2026, 11:58:15 AM | 16172.5s | verified | start_missing | 16
t17-benefit-history | 8/9/2026, 11:58:15 AM | 16172.5s | verified | worker_unmapped | 452
t17-benefit-history | 8/9/2026, 11:58:15 AM | 16172.5s | verified | benefit_unmapped | 6863
t17-benefit-history | 8/9/2026, 11:58:15 AM | 16172.5s | verified | end_before_start | 2553
t17-benefit-history | 8/9/2026, 11:58:15 AM | 16172.5s | verified | relation_unmapped | 71964
t17-benefit-history | 8/9/2026, 11:58:15 AM | 16172.5s | verified | benefit_ref_missing | 41
t17-benefit-history | 8/9/2026, 11:58:15 AM | 16172.5s | verified | employer_unresolved | 1462
t17-benefit-history | 8/9/2026, 11:58:15 AM | 16172.5s | verified | subscriber_worker_mismatch | 69
t16-elections | 8/9/2026, 11:29:39 AM | 1399.8s | verified | start_missing | 3
t16-elections | 8/9/2026, 11:29:39 AM | 1399.8s | verified | worker_unmapped | 234
t16-elections | 8/9/2026, 11:29:39 AM | 1399.8s | verified | benefit_unmapped | 54
t16-elections | 8/9/2026, 11:29:39 AM | 1399.8s | verified | relation_unmapped | 22
t16-elections | 8/9/2026, 11:29:39 AM | 1399.8s | verified | worker_ref_missing | 3
t16-elections | 8/9/2026, 11:29:39 AM | 1399.8s | verified | end_not_after_start | 625
t16-elections | 8/9/2026, 11:29:39 AM | 1399.8s | verified | employer_ref_missing | 2
t17-benefit-history | 8/8/2026, 10:29:04 PM | 17754s | verified | start_missing | 16
t17-benefit-history | 8/8/2026, 10:29:04 PM | 17754s | verified | worker_unmapped | 452
t17-benefit-history | 8/8/2026, 10:29:04 PM | 17754s | verified | benefit_unmapped | 6863
t17-benefit-history | 8/8/2026, 10:29:04 PM | 17754s | verified | end_before_start | 2553
t17-benefit-history | 8/8/2026, 10:29:04 PM | 17754s | verified | relation_unmapped | 71964
t17-benefit-history | 8/8/2026, 10:29:04 PM | 17754s | verified | benefit_ref_missing | 41
t17-benefit-history | 8/8/2026, 10:29:04 PM | 17754s | verified | employer_unresolved | 35103
t17-benefit-history | 8/8/2026, 10:29:04 PM | 17754s | verified | open_end_through_required | 159735
t17-benefit-history | 8/8/2026, 10:29:04 PM | 17754s | verified | subscriber_worker_mismatch | 69
t16-elections | 8/8/2026, 10:25:40 PM | 36.1s | verified | start_missing | 3
t16-elections | 8/8/2026, 10:25:40 PM | 36.1s | verified | worker_unmapped | 234
t16-elections | 8/8/2026, 10:25:40 PM | 36.1s | verified | benefit_unmapped | 54
t16-elections | 8/8/2026, 10:25:40 PM | 36.1s | verified | relation_unmapped | 22
t16-elections | 8/8/2026, 10:25:40 PM | 36.1s | verified | worker_ref_missing | 3
t16-elections | 8/8/2026, 10:25:40 PM | 36.1s | verified | end_not_after_start | 625
t16-elections | 8/8/2026, 10:25:40 PM | 36.1s | verified | employer_ref_missing | 2
t-employer-rates | 8/8/2026, 10:20:32 PM | 2.5s | verified | bad_rate | 2
t-employer-rates | 8/8/2026, 10:20:32 PM | 2.5s | verified | rate_conflict | 1
t-employer-policies | 8/8/2026, 10:13:52 PM | 3.4s | verified | policy_unmapped | 2
t-employer-rates | 8/8/2026, 10:08:57 PM | 4.4s | verified | bad_rate | 2
t-employer-rates | 8/8/2026, 10:08:57 PM | 4.4s | verified | rate_conflict | 1
t-employer-policies | 8/8/2026, 9:56:41 PM | 6.3s | verified | policy_unmapped | 2
t19-payments | 8/8/2026, 7:17:26 PM | 0.8s | verified | date_missing | 1
t19-payments | 8/8/2026, 7:17:26 PM | 0.8s | verified | amount_missing | 102
t19-payments | 8/8/2026, 7:17:26 PM | 0.8s | verified | status_missing | 3
t19-payments | 8/8/2026, 7:17:26 PM | 0.8s | verified | account_unensured | 3
t19-payments | 8/8/2026, 7:17:26 PM | 0.8s | verified | payer_ref_missing | 40
t19-payments | 8/8/2026, 7:17:26 PM | 0.8s | verified | payment_type_missing | 1
t19-payments | 8/8/2026, 7:06:36 PM | 36.4s | verified | date_missing | 1
t19-payments | 8/8/2026, 7:06:36 PM | 36.4s | verified | amount_missing | 102
t19-payments | 8/8/2026, 7:06:36 PM | 36.4s | verified | status_missing | 3
t19-payments | 8/8/2026, 7:06:36 PM | 36.4s | verified | account_unensured | 3
t19-payments | 8/8/2026, 7:06:36 PM | 36.4s | verified | payer_ref_missing | 40
t19-payments | 8/8/2026, 7:06:36 PM | 36.4s | verified | payment_type_missing | 1
t16-elections | 8/8/2026, 6:56:34 PM | 4367.7s | verified | start_missing | 3
t16-elections | 8/8/2026, 6:56:34 PM | 4367.7s | verified | worker_unmapped | 234
t16-elections | 8/8/2026, 6:56:34 PM | 4367.7s | verified | benefit_unmapped | 54
t16-elections | 8/8/2026, 6:56:34 PM | 4367.7s | verified | relation_unmapped | 22
t16-elections | 8/8/2026, 6:56:34 PM | 4367.7s | verified | worker_ref_missing | 3
t16-elections | 8/8/2026, 6:56:34 PM | 4367.7s | verified | end_not_after_start | 625
t16-elections | 8/8/2026, 6:56:34 PM | 4367.7s | verified | employer_ref_missing | 2
t16-elections | 8/8/2026, 6:56:34 PM | 4367.7s | verified | election_type_unmapped | 61823
t15-relationships | 8/8/2026, 6:50:15 PM | 196.1s | verified | alt_worker_unmapped | 7
t15-relationships | 8/8/2026, 6:50:15 PM | 196.1s | verified | owner_has_no_worker | 42
t15-relationships | 8/8/2026, 6:50:15 PM | 196.1s | verified | alt_contact_unmapped | 2
t15-relationships | 8/8/2026, 6:50:15 PM | 196.1s | verified | relation_create_failed | 6
n4-employee-ids | 8/8/2026, 6:31:15 PM | 2.9s | verified | worker_unmapped | 80
n4-employee-ids | 8/8/2026, 6:31:15 PM | 2.9s | verified | employer_unmapped | 4
t18-ledger | 8/8/2026, 6:26:05 PM | 2279.1s | verified | (none)
n4-employee-ids | 8/8/2026, 6:25:48 PM | 9s | verified | worker_unmapped | 80
n4-employee-ids | 8/8/2026, 6:25:48 PM | 9s | verified | employer_unmapped | 4
t15-relationships | 8/8/2026, 6:25:44 PM | 910.6s | verified | alt_worker_unmapped | 7
t15-relationships | 8/8/2026, 6:25:44 PM | 910.6s | verified | owner_has_no_worker | 42
t15-relationships | 8/8/2026, 6:25:44 PM | 910.6s | verified | alt_contact_unmapped | 2
t15-relationships | 8/8/2026, 6:25:44 PM | 910.6s | verified | relation_create_failed | 6
t7t24-employers | 8/8/2026, 5:43:19 PM | 14.1s | verified | phone_invalid | 7
t7t24-employers | 8/8/2026, 5:43:19 PM | 14.1s | verified | duplicate_email | 442
t7t24-employers | 8/8/2026, 5:43:19 PM | 14.1s | verified | shopcontact_no_name | 73
t7t24-employers | 8/8/2026, 5:43:19 PM | 14.1s | verified | shopcontact_employer_unresolved | 5
t27-users | 8/8/2026, 5:36:00 PM | 186.3s | verified | no_resolvable_worker | 335
t27-users | 8/8/2026, 5:36:00 PM | 186.3s | verified | ambiguous_worker_email | 26
t6-member-statuses | 8/8/2026, 5:35:55 PM | 2089.3s | verified | worker_unmapped | 1
t7t24-employers | 8/8/2026, 5:35:42 PM | 28.9s | verified | phone_invalid | 7
t7t24-employers | 8/8/2026, 5:35:42 PM | 28.9s | verified | duplicate_email | 442
t7t24-employers | 8/8/2026, 5:35:42 PM | 28.9s | verified | shopcontact_no_name | 73
t7t24-employers | 8/8/2026, 5:35:42 PM | 28.9s | verified | shopcontact_employer_unresolved | 5
t-policies | 8/8/2026, 5:07:27 PM | 40.2s | verified | policy_ref_not_staged | 1
t-policies | 8/8/2026, 5:07:27 PM | 40.2s | verified | policy_unmatched_unreferenced | 129
t-policies | 8/8/2026, 5:01:54 PM | 55.4s | verified | policy_ref_not_staged | 1
t-policies | 8/8/2026, 5:01:54 PM | 55.4s | verified | policy_unmatched_unreferenced | 129
seed-trust-config | 8/8/2026, 4:42:17 PM | 0.7s | completed | (none)
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | 13542.5s | verified | phone_invalid | 21
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | 13542.5s | verified | contact_no_name | 9
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | 13542.5s | verified | duplicate_email | 10614
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | 13542.5s | verified | ssn_collision_q36 | 1
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | 13542.5s | verified | address_incomplete | 1089
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | 13542.5s | verified | worker_contact_unresolved | 4
t3t1-contacts-workers | 8/8/2026, 1:46:02 PM | 13542.5s | verified | worker_id_value_collision | 17107
t4-options | 8/8/2026, 1:43:24 PM | 0.6s | verified | (none)

## Instructions & Legend
S1 Rehearsal Reject Triage — Instructions & Legend
PURPOSE
This workbook is the triage tracker for the initial S1 rehearsal upload. Every (loader, reject reason) pair from the most recent run of each loader appears as one row in the Triage sheet. Use it to decide what to do with each reject set before the production migration runs.
HOW TO USE
1. Start at the top | Rows are sorted largest-count-first so the highest-impact reject sets come first. Resolved and no-reject rows are at the bottom.
2. Fill Triage Category | Pick one of the five categories below for each open row.
3. Fill Review Status | Set to "In review" while deciding, "Decided" when you have a ruling, "Resolved" when all follow-up work is done.
4. Fill Allow-list? | "yes" = this reason should be added to the --allow-rejects list for the next run. "no" = fix needed first. "n/a" = no-reject / resolved rows.
5. Read the Trend column | Shows counts across runs from oldest → newest. Zero in the latest position means the reject set is already gone. Green rows in Triage are resolved sets (zero in latest run).
6. Grey rows | Loaders that completed with zero rejects in the latest run.
TRIAGE CATEGORIES
Acceptable as-is | The S1 data genuinely contains records that cannot or should not be imported. Rejecting them is correct behavior. Add to --allow-rejects.
S1 data cleanup | Reject caused by bad data in S1 (missing fields, bad formats, orphaned references). Clean the source data and re-run.
Loader script fix | Reject caused by a gap or bug in the loader code. The data could be imported if the script were corrected.
Needs ruling | Unclear which category applies. A human decision or business-rule clarification is required.
Already fixed | The reject appeared in a prior run but the trend shows it has reached zero in the latest run. No further action needed.
REVIEW STATUS
Not reviewed | Default. No one has looked at this row yet.
In review | Someone is actively investigating.
Decided | A triage category and ruling have been assigned.
Resolved | Any follow-up work (cleanup, fix, allow-list addition) is complete.
SHEETS IN THIS WORKBOOK
Triage | One row per (loader, reject reason) from the latest run of each loader. Fill in the right-hand columns to track decisions.
Run History | Every run from the log with all reject reasons and counts. Use to understand trends and history for any specific loader.
Instructions & Legend | This sheet.
FILE METADATA
Log source | attached_assets/Pasted--Run-Started-Duration-Outcome-Rejects-t29-enrollment-pa_1786977106071.txt
Generated | 8/17/2026, 2:39:19 PM
Total loaders | 18
Total triage rows | 56
Total run history rows | 34 runs